## Validation Report
|  | Klug Avalon Mechatronics Pvt. Ltd. |  |  |  |  | Confidential
[7 empty] | Form No. | DNE-F-13
[7 empty] | Revision No. | 01
|  | Title:Validation for PCB TEMP 41 |  |  |  |  | Department | Design and Engineering
[7 empty] | Revision Date | 12.11.2021
PROJECT NAME |  |  | CAN CONTROLLER 1 |  | PROJECT NUMBER
REFERENCE DOCUMENT |  |  | Check list and Test procedure |  | REVIEWED BY
CREATED BY |  |  | Madhav D.. |  | REVIEW DATE
CREATION DATE |  |  |  |  | SIGNATURE
SIGNATURE
S.No. | Test case_ID | Description | Test Objectives | Steps And Data | Expected Result | Actual Result | Status | Remarks (if any)
1 | TC_1_01 | Power Supply | Checking of power supply before and After Filter. | Connect supply +24V on board and switch it ON. | Voltage across C1 and C2 must be +23.9 V to 24.2V. | +24V | OK
2 | TC_1_02 | Power Supply | Checking of+5V supply at the output of regulator U2 (LM2576-5V) | Connect supply on board and switch it ON. | Voltage across C8 must be +4.98 V to 5.2V. | +5V | OK
3 | TC_2 | Microcontroller Testing | Checking PIC18F25K80 programming U9. | Download test hex file in the PIC18F25K80 for testing of all modules of PCB | program downloaded Successfully. | Programmed successfully | OK
4 | TC_3 | CAN Communication 1 | Checking of CAN communication in both transmit and receive U5(MCP 2551) | Connect this PCB with DSPIC PCB( 89344R4) also connect to PC using CANMate | CAN data should be transmitted and received | CAN data transmitted and received | OK
5 | TC_4 | Telematics Interface | Checking Telematics interface in both transmit and receive | Connect this PCB with DSPIC PCB( 89344R4) also connect to PC using USB to TTL. | Transimitted data should receive on PC | Data received on PC. | OK
6 | TC_5 | Input IC (Analog Inputs) | Testing of Input IC (MC 33972) for Analog Inputs | 1) Connect this PCB with DSPIC PCB( 89344R4) 2) Connect this PCB with DSPIC PCB( 89345R4) 2)Connect pot test jig at connector CN2. for P1,P2,Length,Angle Channel. | 1) For P1 and P2 Voltage across C25 and C26 should vary from 0.8V to 4V and counts on display should vary. 2) For Length and Angle Voltage across C27 and C28 should vary from 0 to 5V and counts on display should vary. | Voltages varied and counts are displayed on display | OK
7 | TC_6 | Input IC (Digital Inputs) | Testing of Input IC (MC 33972) for Digital Inputs (Switch to Ground) | 1) Connect this PCB with DSPIC PCB( 89344R4) 2) Connect this PCB with DSPIC PCB( 89345R4) 2) Connect Digital inputs pins to GND. | 1) For Digital Inputs when Inputs are gronded Voltage across C29,C30,C31,C32 capaciotrs should be 0V. 2) LED for particular input should be turn ON. | Voltage across capacitors observed 0V and LED'S are turned ON as per code. | OK
8 | TC_7 | Input IC (Digital Inputs) | Testing of Input IC (MC 33972) for Digital Inputs (Switch to Battery) | 1) Connect this PCB with DSPIC PCB( 89344R4) 2) Connect this PCB with DSPIC PCB( 89345R4) 2) Connect Digital inputs pins to VCC. | 1) For Digital Inputs when Inputs are gronded Voltage across C29,C30,C31,C32 capaciotrs should be VCC . 2) LED for particular input should be turn ON. | Voltage across capacitors observedto VCC and LED'S are turned ON as per code. | OK
9 | TC_8 | Output IC | Testing of Output IC (MC 33996) | Connect supply on board and switch it ON and program the microcontroller with test code. | Digital outputs should be turn ON and OFF as per test code | Digital output turned On and OFF as per test code. | OK
CONCLUSION: Board tested and working as per function.